## Defect Log
Defect ID | Test Case ID | Module | Defect Description | Severity | Priority | Status | Reported By | Date Logged | Assigned To | Resolution/Notes
D-001 | UAT-002 | Payment | Payment confirmation email delayed by 2 minutes | Medium | Medium | Open | Sarah Johnson | 09/08/2025 | Dev Team | Investigating notification queue
D-002 | UAT-003 | Records | Notes not visible until system refresh | High | High | Open | Sarah Johnson | 09/08/2025 | Dev Team | To fix cache sync issue
D-003 | UAT-004 | Performance | System slows after 850 concurrent users | Critical | High | Open | Sarah Johnson | 09/08/2025 | Performance Team | Requires load balancing optimization
D-004 | UAT-005 | Reporting | Monthly report missing payment KPIs | High | High | Open | Sarah Johnson | 09/08/2025 | Reporting Dev | Update report query mapping