## UAT Scripts
Test ID | Requirement ID | Priority | Module | Test Scenario | Precondition | Test Steps | Expected Result | Actual Result | Status (Pass/Fail) | Tester Comments
UAT-001 | FR3 | High | Appointment | Verify patient can book appointment online | Patient is registered & logged in | 1. Log in 2. Navigate to Book Appointment 3. Select doctor & slot 4. Confirm appointment | Appointment booked, confirmation email sent | Appointment booked successfully, confirmation email received instantly | Pass | Works as expected
UAT-002 | FR7 / FR8 | High | Payment | Verify payment gateway processes payment | Patient has valid card | 1. Book appointment 2. Choose Pay Online 3. Enter card details 4. Submit payment | Payment processed, receipt generated, confirmation sent | Payment processed, receipt generated, email delayed by 2 minutes | Pass w/Issue | Email latency observed
UAT-003 | FR6 | Medium | Records | Verify doctors can update patient records | Appointment completed | 1. Log in as Doctor 2. Open patient record 3. Add treatment notes 4. Save changes | Updated records visible in patient portal | Notes saved but not visible in patient portal until refresh | Fail | Data sync issue
UAT-004 | NFR4 | High | Performance | Verify system supports 1,000 concurrent users | Load test environment ready | 1. Simulate 1,000 logins 2. Monitor booking, payment, and records modules | System remains responsive, no crashes or slowdowns | System slowed significantly after 850 concurrent users | Fail | Performance bottleneck
UAT-005 | FR10 | Medium | Reporting | Verify system generates monthly usage report | Manager has access rights | 1. Log in as Manager 2. Navigate to Reports 3. Select Monthly Usage | Report generated with accurate data and KPIs | Report generated but missing KPIs for payment transactions | Fail | Data mapping issue in report

## Feedback Form
Project Name: | Patient Management System
Tester Name: | Jamie Christian II
Date: | 09/08/2025
Module Tested: | ☑ Appointment Booking ☑ Payment ☐ Medical Records ☑ Reporting
Test Case ID(s): | UAT-001, UAT-002, UAT-005
Was functionality working as expected? | ☑ Yes ☐ No
Priority of Issues Found: | ☑ High ☐ Medium ☐ Low
Rate the system (1–5): | ⭐⭐⭐⭐ (4/5)
Feedback / Issues: | - Payment email confirmations delayed. - Monthly report missing payment KPIs.
Suggestions for Improvement: | - Optimize notification service to reduce email latency. - Fix report data mapping to include all KPIs.
Signature: | Jamie Christian II.