## Stakeholder Identification
Stakeholder | Role/Responsibility
Patients | Book appointments, make payments, access records
Clinic Staff | Schedule appointments, update records, process billing
Doctors | Provide medical care, update medical records
IT Team | Develop, maintain, and integrate the system
System Analyst | Requirements gathering, documentation, process modeling
Clinic Manager | Oversees daily operations, resource allocation
Payment Gateway Vendor | Provides secure online payment processing
Regulatory Bodies | Ensure HIPAA & PCI DSS compliance

## Influence_Interest_Grid
Category | Stakeholders | Engagement Strategy
High Influence / High Interest | Clinic Manager, IT Team, System Analyst | Collaborate closely, involve in decisions, provide regular updates
High Influence / Low Interest | Regulatory Bodies, Payment Vendor | Keep satisfied, ensure compliance, provide summary reports
Low Influence / High Interest | Patients, Clinic Staff, Doctors | Keep informed, gather feedback regularly, provide training/support
Low Influence / Low Interest | External Partners (if any) | Minimal effort, send high-level updates

## RACI Matrix
Activity/Deliverable | Patients | Staff | Doctors | Clinic Manager | IT Team | Analyst | Payment Vendor | Reg. Bodies
Requirements Gathering | C | C | C | A | C | R | I | I
System Design | I | I | I | A | R | R | C | C
Appointment Booking Feature | R | R | C | A | R | R | I | I
Payment Integration | I | I | I | A | R | R | R | C
Regulatory Compliance | I | I | I | A | C | R | C | R
Training & Rollout | R | R | R | A | C | R | I | I