## Sheet1
Section | Description | Example for XYZ Health Solutions
Project Title | Name of the project | XYZ Health Solutions IT System Integration
Date | Date the charter is created | Q3, 2025
Project Description | Brief overview of the project’s purpose and scope | Implement a unified IT system that integrates patient records, scheduling, and billing. Use MySQL for storage, a data warehouse for analytics, and Tableau for dashboards. Ensure HIPAA compliance and operational efficiency.
Objectives | Specific, measurable goals of the project. | 1) Ensure HIPAA compliance across all modules. 2) Reduce scheduling errors by 20% within 6 months. 3) Increase patient satisfaction scores by 10% within 12 months. 4) Achieve zero unplanned downtime during system cutover.
Success Criteria | Measurable outcomes to define project success. | • Improve patient satisfaction by 10% in 12 months. • Reduce scheduling errors by 20% in 6 months. Improve patient satisfaction by 10% in 12 months. • Ensure HIPAA compliance. • Provide real-time dashboards. • Deliver on time and within budget.
High-Level Requirements | Key functional and technical requirements | • Centralized patient record system. • Appointment scheduling with reminders. • Integrated billing and payments. • Role-based access controls. • Data warehouse and Tableau dashboards. • 99.9% uptime.
Key Stakeholders and roles | List of stakeholders with roles and responsibilities | • Dr. Maria Thompson (CEO, Sponsor) • Liam Carter (Project Manager) • Compliance Officer (HIPAA oversight) • IT Director (System architecture) • Clinic Staff (System users) • Patients (End users)
Scope | In-scope and out-of-scope items | In-scope: Integration of patient, scheduling, and billing systems; staff training; compliance verification. Out-of-scope: Legacy system retirement, hardware upgrades beyond integration needs.
Deliverables | Tangible outputs of the project | In-Scope: Integration of patient records, scheduling, billing, database, dashboards, and compliance checks. Out-of-Scope: Legacy hardware replacement, third-party clinics.
Assumptions | Conditions assumed to be true | • Current infrastructure can support integration. • Stakeholders available for workshops. • Staff and patients will adopt system.
Constraints | Limitations or restrictions on the project | • HIPAA regulations • Budget & timeline limits • Minimal downtime allowed
High-Level Risks | Potential risks that could impact the project | • Data migration errors • Staff resistance to adoption • Compliance/audit delays • Integration complexity
Milestones | Key dates for major project phases | Q4, Current year: Requirements finalized. Q1 Next year: System testing. Q2, Next year: Launch.
Budget | Estimated financial resources required | To be determined by project sponsor (not specified in scenario).
Approval | Signatures or approval fields for key stakeholders | Dr. Maria Thompson (CEO), Liam Carter (PM).